## Model
Simulation based optimisation of resource usage and project project prioritisation - By Mukul Pareek, EMBA-Global 2003
Skills requirements, by project
Project name (taken from real order book) | Project number | PM | Dev | BA | DBA |  | Client's reservation price | Est cost | Project duration | Profit | Value added % | Earliest Start | Latest Start | Value added per month | Actual start | End date |  | Work area - ignore
GL report for UK | 1 | 0 | 1 | 1 | 0 |  | 50 | 12 | 1 | 38 | 316.7% | 1 | 4 | 38 | 2 | 2 | Blue cells require data entry | 2
EFT for Belgium | 2 | 0 | 1 | 1 | 0 |  | 75 | 24 | 2 | 51 | 212.5% | 3 | 6 | 25.5 | 4 | 5 | Black cells are calculated cells | 4
Interface for Singapore | 3 | 0 | 1 | 1 | 1 |  | 50 | 36 | 2 | 14 | 38.89% | 11 | 13 | 7 | 0 | 0 | Red cells represent optimum solution | 0
Italy customers report | 4 | 0 | 1 | 1 | 0 |  | 25 | 24 | 2 | 1 | 4.167% | 6 | 9 | 0.5 | 8 | 9 |  | 8
Greece fiscal reports | 5 | 1 | 2 | 1 | 0 |  | 150 | 72 | 3 | 78 | 108.3% | 2 | 3 | 26 | 2 | 4 |  | 2
Changeover to Euro | 6 | 1 | 2 | 1 | 1 |  | 200 | 90 | 3 | 110 | 122.2% | 4 | 7 | 36.6667 | 4 | 6 | Key to skills: | 4
Currency change for CH | 7 | 0 | 0 | 1 | 0 |  | 50 | 6 | 1 | 44 | 733.3% | 7 | 8 | 44 | 7 | 7 | PM = Project Management | 7
R11i Benelux | 8 | 1 | 2 | 3 | 1 |  | 300 | 168 | 4 | 132 | 78.57% | 3 | 5 | 33 | 0 | 0 | Dev = Development (programming) | 0
R11i Nordics | 9 | 1 | 2 | 2 | 1 |  | 250 | 108 | 3 | 142 | 131.5% | 5 | 7 | 47.3333 | 5 | 7 | BA = Business Analysis | 5
R11i UK | 10 | 2 | 3 | 4 | 1 |  | 600 | 240 | 4 | 360 | 150% | 8 | 10 | 90 | 8 | 11 | DBA = Database Administrator | 8
R11i Singapore | 11 | 1 | 2 | 3 | 1 |  | 200 | 126 | 3 | 74 | 58.73% | 10 | 13 | 24.6667 | 12 | 14 |  | 12
[13 empty] | Total value added: |  | 336 |  |  | 336
Other inputs into the model: |  |  | Value | Comments
Max shortage allowed before contractors are hired |  |  | 1 | Staff shortages affect project success and client perception. Small shortages can be managed with existing staff. | [12 empty] | Reservation price: Maximum a client
Contractor cost per month |  |  | 25 | in GBPs per month | [12 empty] | will pay for a project.
Staff cost per month |  |  | 6 | in GBPs per month | [12 empty] | Est Cost: Staff employed x number of
months x cost per staff per month
Staff availability and usage | [16 empty] | Earliest and Latest start dates: relate
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | to each project
| Staff | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Available skills: number of staff for
Available skills | PM | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | each skill type available each month
| Dev | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| BA | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| DBA | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Used skills | PM | 0 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0
(Based on project start | Dev | 0 | 3 | 2 | 5 | 5 | 4 | 2 | 4 | 4 | 3 | 3 | 2 | 2 | 2 | 0
dates and schedule as | BA | 0 | 2 | 1 | 3 | 4 | 3 | 3 | 5 | 5 | 4 | 4 | 3 | 3 | 3 | 0
below) | DBA | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Over/under utilisation
| PM | 2 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2
| Dev | 2 | -1 | 0 | -3 | -3 | -2 | 0 | -2 | -2 | -1 | -1 | 0 | 0 | 0 | 2
| BA | 3 | 1 | 2 | 0 | -1 | 0 | 0 | -2 | -2 | -1 | -1 | 0 | 0 | 0 | 3
| DBA | 1 | 1 | 1 | 0 | -1 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Penalty for shortages:
Total shortages: |  | 0 | -1 | 0 | -3 | -5 | -3 | 0 | -4 | -4 | -2 | -2 | 0 | 0 | 0 | 0
Shortage to be filled in by contract resource |  | 0 | 0 | 0 | 2 | 4 | 2 | 0 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0
Unutilised staff |  | 8 | 3 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 8
Schedule of ongoing projects: (shows which projects are going on in which month, 1 indicates ongoing, 0 (zeros have been conditionally formatted to be not visible below) indicates not happening in that month)
| Project | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
| 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0
Objective function to maximise: (amounts in GBP)
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Value addition from jobs | 898 | 0 | 64 | 26 | 88.1667 | 109.5 | 84 | 91.3333 | 90.5 | 90.5 | 90 | 90 | 24.6667 | 24.6667 | 24.6667 | 0
Penalty for contractor hire | 400 | 0 | 0 | 0 | 50 | 100 | 50 | 0 | 75 | 75 | 25 | 25 | 0 | 0 | 0 | 0
Cost of unused staff | 162 | 48 | 18 | 24 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 48
Total value add | 336 | -48 | 46 | 2 | 38.1667 | 9.5 | 34 | 85.3333 | 15.5 | 15.5 | 65 | 65 | 18.6667 | 18.6667 | 18.6667 | -48
Run Simulation